## Sheet1
2023-10-17 | Tasks need to be finished till 2:00 AM IST
To-Do | Who's Doing | Done | Not Done Reason
Create Business Analyst resume research document | Umang | Yes
Create Data Analyst resume research document | Krishan | Yes
Create Front-End, Full Stack resume research document | Abhinab | Yes
Create Data Engineer resume research document | Vishwa | Yes
Create Quality Analyst resume research document | Mayank | Yes
Create Cloud Engineer resume research document | Harsh | Yes
Convert the ipynb file given by Umang of yashita's assessment to pdf as a research document | Umang | Yes
Create Agile document for TMS, with Sprints, Stories and Backlog | Mayank | No | Mayank was consumed in Mock calls and will be finished till EOD
Create Login Page for TMS | Abhinab | Yes
Need to tune the resume assigning script | Umang | Yes
Need to add Reassigned category in SQL status table | Umang | Yes
Need to finish the Uber task | Vishwa | No | The task given to vishwa is a Data Engineer task and is difficult for her since it is out of her expertise being a data analyst.
2023-10-18 | Tasks need to be finished till 2:00 AM IST
To-Do | Who's Doing | Done | Remarks
Need to add new Acknowledgement table in Database and foreign key of the same in main table | Umang | Yes
Create resume as discussed at the EOD on 10/17/2023 | Umang | Yes
Need to have discussion and bring solution for the skewed decision coming from algorithm | Umang | Yes
Need to learn and apply Pandas | Vishwa | No | On Going task
Working on New Page Component of TMS to move assignees after assignment | Abhinab | Yes
Giving training to a candidates | Krishan | Yes
Need to correct the resume | Mayank | Yes
Need to sit with Valish for Sprint discussion | Mayank | Yes
Agile document should be completed | Mayank | Yes
Documentation on training syllabus of all the profiles | Mayank | Yes | Additional Task
Working on mail parser ETL | Harsh | No | On Going Task ,Was consumed on lot of candidate Calls
Starting to work on Forage Project for training | Aakash | Yes
Starting to work on Forage Project for training | Karan | Yes
2023-10-19 | Tasks need to be finished till 2:00 AM IST
To-Do | Who's Doing | Done | Remarks
Need to get familiar with Supabase making sure all the data are inserted correctly with constraints | Umang
Testing the Host of Supabase in python | Umang
Create report for Light Manager | Mayank
Giving Interview Supports | Abhinab
Deploying in Vercel | Abhinab
Giving a training session | Krishan
Working on Forage Assessment | Krishan
Working on Forage Assessment | Karan
Working on Forage Assessment | Aakash
Continuing Training of pandas | Vishwa
Azure fundamentals and integration training and application | Harsh
Giving Interview Supports | Harsh